## Slide 1: Enabling ITS2 in Adobe AEM and Apache Sling/Jackrabbit
Des Oates | Engineering Manager | Adobe

## Slide 2: What To Expect Today
The Proposed Implementation
Where We Are Now
Deliverables and Expectations

## Slide 3: The Implementation Proposal
Open Standard
Open
Source
Proprietary
Apache Sling
Apache Jackrabbit
Adobe Experience Manager
Content Repository Extreme
JSR 283 (JCR 2.0)
Java Content Repository
ITS2
ITS2

## Slide 4: Where Are We Now
Started!
  Resources Onboarded
  Designs Proposed and Reviewed
  Work Started on 1st two data categories:
    Translate
    Localization Note

## Slide 5: Where Are We Now
  Delayed by around 3 to 4 months
    Staff Rotation
    Finding the Resources
    Business Priorities

## Slide 6
April
Resource on boarding.
Design draft.
June
1st prototype:
Global rules
Translate
L10n Note
sling:resourceSuperType
JCR store/retrieve
HTML export
May
First sprints begin.
Design approved.
Begin open source Legal process.
July
2nd prototype:
Global rules
IDValue/ IDValueRule
TargetPointer/
TargetPointerRule
Legal check-in
August
3nd prototype
Local rules
4 data categories
Extend Sling GET
HTML/XLIF export & import
September
Release to W3C.
Submit to Apache Foundation.
Consultation
High Level Design
Distribution Phase
Project X Timeline to Market
Project Timeline
Project Start Date
Project Deadline
Development Phase
changes:
Focus on Apache Sling rather than JackRabbit

## Slide 7: Deliverables and Expectations
Monthly Sprints – Incremental deliverables
June 2013: First working prototype
  2 categories implemented
    LocNote and Translate
    Global Rules
    HTML
    Store and Retrieve Content to/from CMS
  Demo to Stakeholders Call in June 26th

## Slide 8: Deliverables and Expectations
Two intermediate releases in July and August
September 2013: Final Release
  4 categories implemented
    LocNote ,Translate, IDValue, and TargetPointer
    Local and Global Rules
    HTML and XLIFF support
    store and retrieve from CMS
  Validated against the Test Suite
  Demo to Stakeholders if required
  Submit source to Apache Foundation

## Slide 9: In Summary
Slow start but we are now up and running
First prototype demo available by late June 2013
Final deliverable due late September 2013